## PCC_PMR 2020 (2nd sem)
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Philippine Carabao Center Procurement Monitoring Report (January to June 2021)
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
OTHER SHOPPING | [43 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES FOR MILK SUPPLEMENTATION PROGRAM | [19 empty] | NBDH-CBEDS | No | Shopping(b) | N/A | N/A | N/A | N/A | 2020-12-04 | 2020-12-04 | N/A | 2020-12-04 | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-01-15 | 2021-01-15 | GAA | 23900 | 23900 | 0 | 4950 | 4950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES | [19 empty] | PROC | No | Shopping(b) | N/A | N/A | N/A | N/A | 2021-01-20 | 2021-01-20 | N/A | 2021-01-20 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | GAA | 10485 | 10485 | 0 | 5721 | 5721 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DIRECT CONTRACTING (ABOVE 50K) | [43 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS OF MITSUBISHI SKY-605 | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 11/18/0220 | 11/18/0220 | N/A | 11/18/0220 | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2020-11-05 | 2020-11-05 | GAA | 54432.91 | 54432.91 | 0 | 54432.91 | 54432.91 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SPECIFIC REAGENTS FOR VET AUTO HEMATOLOGY ANALYZER | [19 empty] | GAA | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-04-14 | 2021-04-14 | GAA | 58000 | 58000 | 0 | 58000 | 58000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE OF MITSUBISHI L200 FB VAN (SLG-626) | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-03-26 | 2021-03-26 | N/A | 2021-03-26 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-03-26 | 2021-03-26 | GAA | 75000 | 75000 | 0 | 5319.63 | 5319.63 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND CALIBRATION OF LABORATORY EQUIPMENT | [19 empty] | RPS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-11-04 | 2020-11-04 | N/A | 2020-11-04 | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-12-17 | 2020-12-17 | GAA | 78400 | 78400 | 0 | 78400 | 78400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BIO-RAD LABORATORY | [19 empty] | ABGS | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-03-24 | 2021-03-24 | GAA | 91370 | 91370 | 0 | 72700 | 72700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR & REPLACEMENT OF PARTS OF TRANSBOLT TURBO | [19 empty] | RPS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-29 | 2021-01-29 | N/A | 2021-01-29 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-03-19 | 2021-03-19 | GAA | 113700 | 113700 | 0 | 114000 | 114000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| KONIKA MINOLTA BIZHUB COPIER | [19 empty] | VARIOUS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2/18/2021 | 2/18/2021 | N/A | 2/18/2021 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-12 | 2021-03-12 | GAA | 134932.8 | 134932.8 | 0 | 131670 | 131670 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CONSUMABLES FOR MILKING PARLOR | [19 empty] | GP | No | Direct Contracting | N/A |  | N/A | N/A | 2020-11-27 | 2020-11-27 | N/A | 2020-11-27 | 2021-01-18 | 2021-01-18 | 2021-01-18 | 2021-04-14 | 2021-04-14 | GAA | 186570 | 186570 | 0 | 186570 | 186570 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE OF MILLI- Q INTEGRAL 5 | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-12-10 | 2020-12-10 | N/A | 2020-12-10 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-03-17 | 2021-03-17 | GAA | 340000 | 340000 | 0 | 339500 | 339500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CHEMICALS & LUBRICANTS FOR FARM MACHINE | [19 empty] | GP/LBRAF | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-02-26 | 2021-02-26 | N/A | 2021-02-26 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 | GAA | 380388.96 | 380388.96 | 0 | 380388.96 | 380388.96 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROMEGA PRODUCTS | [19 empty] | VARIOUS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2/19/2021 | 2/19/2021 | N/A | 2/19/2021 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-05-14 | 2021-05-14 | GAA | 394655.81 | 394655.84 | 0 | 347443.85 | 347443.85 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROMEGA REAGENTS AND SUPPLIES | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-12-02 | 2020-12-02 | N/A | 2020-12-02 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-03-08 | 2021-03-08 | GAA | 713266 | 713266 | 0 | 567474.5 | 567474.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANNUAL PREVENTIVE MAINTENANCE FOR APPLIED BIOSYSTEMS 3500 | [19 empty] | ABGS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-12-07 | 2020-12-07 | N/A | 2020-12-07 | 2021-01-08 | 2021-01-08 | 2021-01-08 | 2021-02-04 | 2021-02-04 | GAA | 716000 | 716000 | 0 | 716000 | 716000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DIRECT CONTRACTING (BELOW 50K) | [43 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS AND CALIBRATION OF FUJI DRI-CHEM MACHINE NX500 | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-19 | 2021-01-19 | N/A | 2021-01-19 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-23 | 2021-03-23 | GAA | 6000 | 6000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DRUM DR312 (FOR KONICA MINOLTA DEVELOP INEO 367 COPIER) | [19 empty] | PROC | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-11-24 | 2020-11-24 | N/A | 2020-11-24 | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2020-12-15 | 2020-12-15 | GAA | 9500 | 9500 | 0 | 9500 | 9500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS ISUZU D-MAX | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-13 | 2021-01-13 | N/A | 2021-01-13 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-01-12 | 2021-01-12 | GAA | 10393.35 | 10393.35 | 0 | 10393.35 | 10393.35 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SMART ID PRINTER RIBBON | [19 empty] | HRMS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-03-01 | 2021-03-01 | N/A | 2021-03-01 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-12 | 2021-04-12 | GAA | 12400 | 12400 | 0 | 12400 | 12400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE OF COMPLETE BLOOD ANALYZER DRI-CHEM | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-03-04 | 2021-03-04 | N/A | 2021-03-04 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-05-21 | 2021-05-21 | GAA | 18000 | 18000 | 0 | 18000 | 18000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SPARE PARTS FOR THE REPAIR OF KONICA MINOLTA BIZHUB 283 COPIER | [19 empty] | PROC & RPS | No | Direct Contracting | N/A | N/A | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-14 | 2021-05-14 | GAA | 18142 | 18142 | 0 | 18142 | 18142 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DNA SYNTHESIS KITS FOR 2021 | [19 empty] | BES/RPS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-03-23 | 2021-03-23 | N/A | 2021-03-23 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-27 | 2021-05-27 | GAA | 31645.19 | 31645.19 | 0 | 25310 | 25310 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS OF MITSUBISHI L200 | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-10-02 | 2021-10-02 | N/A | 2021-10-02 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2020-11-25 | 2020-11-25 | GAA | 33369.89 | 33369.89 | 0 | 33369.89 | 33369.89 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GENUINE PARTS FOR SKID LOADER | [19 empty] | GP | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-11-27 | 2020-11-27 | N/A | 2020-11-27 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-02-01 | 2021-02-01 | GAA | 36000 | 36000 | 0 | 35570 | 35570 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DNTP MIXTURE | [19 empty] | CRYO | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-03-03 | 2021-03-03 | GAA | 38775 | 38775 | 0 | 35250 | 35250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CERTIFICATION OF BIOLOGICAL SAFETY CABINET BASED ON NSF 49 OR EN 12469:2000 AND VALIDATION OF CO2 INCUBATOR | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 4/16/2021 | 4/16/2021 | N/A | 4/16/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 | 2021-06-27 | 2021-06-27 | GAA | 40000 | 40000 | 0 | 35112 | 35112 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| KONIKA MINOLTA BIZHUB COPIER | [19 empty] | PROC | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-30 | 2021-03-30 | GAA | 40061 | 40061 | 0 | 40061 | 40061 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PARTS OF MASSEY TRACTOR | [19 empty] | GP | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-10-21 | 2020-10-21 | N/A | 2020-10-21 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2021-01-22 | 2021-01-22 | GAA | 46870 | 46870 | 0 | 46210 | 46210 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS NISSAN URVAN | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-11-11 | 2020-11-11 | N/A | 2020-11-11 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-11-20 | 2020-11-20 | GAA | 49250.02 | 49250.02 | 0 | 49250.02 | 49250.02 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEGOTIATED PROCUREMENT (SMALL VALUE PROCUREMENT ABOVE 50K) | [43 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RETRACTABLE/COLLAPSIBLE TENTS | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 3/29/0221 | 3/29/0221 | N/A | 3/29/0221 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | GAA | 52000 | 52000 | 0 | 47200 | 47200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF MCBOOK PRO-SCREEN REPLACEMENT | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2020-10-06 | N/A | N/A | 2020-11-27 | 2020-11-27 | N/A | 2020-11-27 | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2020-11-17 | 2020-11-17 | GAA | 56000 | 56000 | 0 | 34500 | 34500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS & TOKEN FOR VALENTINES CELEBRATION | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | GAA | 60000 | 60000 | 0 | 44400 | 44400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LEARNING AND DEVELOPMENT PROVIDER | [19 empty] | HRMS | No | Small Value Procurement | N/A | 2021-02-19 | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-03-04 | 2021-03-04 | GAA | 65000 | 65000 | 0 | 64500 | 64500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HIGH FIDELITY PRIMERS | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2020-10-06 | N/A | N/A | 2020-10-09 | 2020-10-09 | N/A | 2020-10-09 | 2020-12-18 | 2020-12-18 | 2020-12-18 | 2021-01-26 | 2021-01-26 | GAA | 65015 | 65015 | 0 | 42628.8 | 42628.8 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CALIBRATION OF VARIOUS REFRIGERATORS, CENTRIFUGE & LYPHILIZER | [19 empty] | BES | No | Small Value Procurement | N/A | 2021-02-11 | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-29 | 2021-03-29 | GAA | 70000 | 70000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TOKEN 62 PCS JACKET | [19 empty] | ACCTG | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2/16/2021 | 2/16/2021 | N/A | 2/16/2021 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-26 | 2021-03-26 | GAA | 74400 | 74400 | 0 | 58900 | 58900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUTTOMIZED POLO SHIRT | [19 empty] | GAD | No | Small Value Procurement | N/A |  | N/A | N/A | 03/15/2021 | 03/15/2021 | N/A | 03/15/2021 | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-03-21 | 2021-03-21 | GAA | 75000 | 75000 | 0 | 33900 | 33900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND REPLACEMENT OF TIRES OF TOYOTA LAND CRUISER (SFV-408) | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-26 | 2021-03-26 | N/A | 2021-03-26 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 | GAA | 75000 | 75000 | 0 | 49000 | 49000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR AND MAINTENANCE OF VARIOUS PCC VEHICLES | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-12-04 | 2021-12-04 | N/A | 2021-12-04 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | GAA | 75000 | 75000 | 0 | 44300 | 44300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANIMAL FEED SUPPLEMENTS (20 BAGS MILK REPLACER) | [19 empty] | GP | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-21 | GAA | 84000 | 84000 | 0 | 84000 | 84000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE APPLIANCES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-05-02 | 2021-05-02 | N/A | 2021-05-02 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-19 | 2021-03-19 | GAA | 84684 | 84684 | 0 | 82990 | 82990 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT EQUIPMENT | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-30 | 2021-03-30 | GAA | 85000 | 85000 | 0 | 80890.6 | 80890.6 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FIELD & LABORATORY PPE'S | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-05-02 | 2021-05-02 | N/A | 2021-05-02 | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-05-24 | 2021-05-24 | GAA | 87800 | 87800 | 0 | 68170 | 68170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RUBBER BOOTS, BLACK (VARIOUS SIZES, MUST PROVIDE SAMPLE FOR SIZING) | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-20 | N/A | N/A | 2021-04-16 | 2021-04-16 | N/A | 2021-04-16 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-31 | 2021-05-31 | GAA | 90450 | 90450 | 0 | 16660 | 16660 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS 74TH PCC MEETING | [19 empty] | OPERATIONS | No | Small Value Procurement | N/A | 2021-01-30 | N/A | N/A | 2021-02-02 | 2021-02-02 | N/A | 2021-02-02 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-05 | 2021-02-05 | GAA | 95000 | 95000 | 0 | 45510 | 45510 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS AND SNCACKS FOR R&D SYMPOSIUM | [19 empty] | RDD | No | Small Value Procurement | N/A | 2020-11-27 | N/A | N/A | 2020-12-01 | 2020-12-01 | N/A | 2020-12-01 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-04 | 2020-12-04 | GAA | 96000 | 96000 | 0 | 96000 | 96000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR COOPERATIVE MANAGEMENT AND GOVERNANCE, AND RISK AND CREDIT MANAGEMENT TRAINING | [19 empty] | SEPS | No | Small Value Procurement | N/A | 2021-02-27 | N/A | N/A | 2021-03-03 | 2021-03-03 | N/A | 2021-03-03 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-10 | 2021-03-10 | GAA | 99000 | 99000 | 0 | 94050 | 94050 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS WITH DELIVERY OF TRAINING MATERIALS AND TOKEN FOR TRAINING ON BASIC AND ADVANCE LINUX | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2021-01-20 | N/A | N/A | 2021-05-02 | 2021-05-02 | N/A | 2021-05-02 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-26 | 2021-02-26 | GAA | 100000 | 100000 | 0 | 42560 | 42560 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT EQUIPMENT | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-03-20 | 2021-03-20 | 2021-03-20 | 2021-04-24 | 2021-04-24 | GAA | 100000 | 100000 | 0 | 98000 | 98000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRINTING AND DELIVERY OF MONOGRAPH | [19 empty] | KMD | No | Small Value Procurement | N/A | 2021-04-21 | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-17 | 2021-06-17 | GAA | 100000 | 100000 | 0 | 43950 | 43950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SANDO BAG....ICE CHEST, STYRO | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-05-06 | 2021-05-06 | N/A | 2021-05-06 | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-05-07 | 2021-05-07 | GAA | 129927 | 129927 | 0 | 112852 | 112852 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| STEEL DOOR CABINETS | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-27 | N/A | N/A | 2021-02-09 | 2021-02-09 | N/A | 2021-02-09 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-04-23 | 2021-04-23 | GAA | 132000 | 132000 | 0 | 127520 | 127520 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CALIBRATION AND MAINTENANCE OF LABORATORY EQUIPMENTS | [19 empty] | CRYO | No | Small Value Procurement | N/A | 2020-10-22 | N/A | N/A | 2020-10-26 | 2020-10-26 | N/A | 2020-10-26 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-02-01 | 2021-02-01 | GAA | 133110 | 133110 | 0 | 104500 | 104500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MINERAL MIX | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 2021-04-07 | 2021-04-07 | GAA | 146400 | 146400 | 0 | 137250 | 137250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANNUAL REEWAL SUBSCRIPTION FIREWALL PROTECTION | [19 empty] | ICTS | No | Small Value Procurement | N/A | 2021-01-16 | N/A | N/A | 2021-01-21 | 2021-01-21 | N/A | 2021-01-21 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-03-02 | 2021-03-02 | GAA | 147000 | 147000 | 0 | 147000 | 147000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICE CHEST STYRO BOXES | [19 empty] | NDBH-CBEDS | No | Small Value Procurement | N/A | 2020-11-07 | N/A | N/A | 2020-11-17 | 2020-11-17 | N/A | 2020-11-17 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-02-11 | 2021-02-11 | GAA | 150000 | 150000 | 0 | 137500 | 137500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE TABLES AND CHAIRS | [19 empty] | ACCTG | No | Small Value Procurement | N/A | 2020-10-06 | N/A | N/A | 2020-11-20 | 2020-11-20 | N/A | 2020-11-20 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-30 | 2021-03-30 | GAA | 154500 | 154500 | 0 | 147000 | 147000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT EQUIPMENT | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-19 | 2021-04-19 | GAA | 160000 | 160000 | 0 | 157800 | 157800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANNUAL MAINTENANCE OF FIRE ALARM SYSTEM | [19 empty] | GSS | No | Small Value Procurement | N/A | 2020-10-28 | N/A | N/A | 2020-11-02 | 2020-11-02 | N/A | 2020-11-02 | 2020-12-28 | 2020-12-28 | 2020-12-28 | 2021-01-19 | 2021-01-19 | GAA | 162960 | 162960 | 0 | 152846.4 | 152846.4 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS & CALIBRATION OF VARIOUS LABORATORY EQUIPMENT AND PIPETTORS | [19 empty] | BES | No | Small Value Procurement | N/A | 2021-01-26 | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-03-09 | 2021-03-09 | GAA | 180000 | 180000 | 0 | 169750 | 169750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR MAIN GATE GUARD HOUSE | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-01-20 | N/A | N/A | 2021-02-11 | 2021-02-11 | N/A | 2021-02-11 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-04-15 | 2021-04-15 | GAA | 200000 | 200000 | 0 | 194500.88 | 194500.88 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FABRIC SOFTENER, 1L....WASHROOM DISINFECT (5L) | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-04-22 | 2021-04-22 | N/A | 2021-04-22 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-27 | 2021-05-27 | GAA | 232230.06 | 232230.06 | 0 | 11030 | 11030 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BATH SOAP, FAMILY GERM PROTECTION 60G....SHAMPOO 300ML | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-04-22 | 2021-04-22 | N/A | 2021-04-22 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-06-24 | 2021-06-24 | GAA | 232230.06 | 232230.06 | 0 | 184290 | 184290 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF 40HP DVMS AIRCON AT LIB COMPLEX | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-02-03 | N/A | N/A | 02/17/2021 | 02/17/2021 | N/A | 02/17/2021 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-05-06 | 2021-05-06 | GAA | 255765.65 | 255765.65 | 0 | 253299.2 | 253299.2 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT SUPPLIES | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2020-10-08 | N/A | N/A | 2020-11-03 | 2020-11-03 | N/A | 2020-11-03 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-26 | 2021-02-26 | GAA | 286940 | 286940 | 0 | 250326 | 250326 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR 0F DAMAGED STRUCTURES | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-01-16 | N/A | N/A | 2021-02-11 | 2021-02-11 | N/A | 2021-02-11 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-04-05 | 2021-04-05 | GAA | 290000 | 290000 | 0 | 278509.39 | 278509.39 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED POLO SHIRTS FOR PCC ANNIVERSARY | [19 empty] | OED (ANNIVERSARY) | No | Small Value Procurement | N/A | 2021-03-12 | N/A | N/A | 2021-03-16 | 2021-03-16 | N/A | 2021-03-16 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-04 | 2021-06-04 | GAA | 300000 | 300000 | 0 | 251250 | 251250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE AND LABORATORY FURNITURE AND FIXTURE | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-11-03 | 2021-11-03 | N/A | 2021-11-03 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-05-17 | 2021-05-17 | GAA | 317160 | 317160 | 0 | 298220 | 298220 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AI BULL LOAN SERVICE RECEIPT | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2021-01-13 | N/A | N/A | 2021-01-20 | 2021-01-20 | N/A | 2021-01-20 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-04-12 | 2021-04-12 | GAA | 350000 | 350000 | 0 | 256130 | 256130 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CALIBRATION OF LABORATORY EQUIPMENTS | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2020-10-22 | N/A | N/A | 2020-10-26 | 2020-10-26 | N/A | 2020-10-26 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-02-01 | 2021-02-01 | GAA | 400000 | 400000 | 0 | 200400 | 200400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT SUPPLIES | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2020-02-05 | N/A | N/A | 2020-11-03 | 2020-11-03 | N/A | 2020-11-03 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-03-25 | 2021-03-25 | GAA | 420600 | 420600 | 0 | 415500 | 415500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE OF MITSUBISHI L200 FB VAN (SKY 616) | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-25 | 2021-03-25 | N/A | 2021-03-25 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-28 | 2021-04-28 | GAA | 500000 | 500000 | 0 | 46000 | 46000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE OF TOYOTA INNOVA (SJJ-409) | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-19 | 2021-03-19 | N/A | 2021-03-19 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-28 | GAA | 500000 | 500000 | 0 | 46000 | 46000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR AND MAINTENANCE OF PCC VEHICLES | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-05 | 2021-05-05 | N/A | 2021-05-05 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | GAA | 500000 | 500000 | 0 | 39600 | 39600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CLEANING SUPPLIES | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-04-20 | N/A | N/A | 2021-04-23 | 2021-04-23 | N/A | 2021-04-23 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-31 | 2021-05-31 | GAA | 608000 | 608000 | 0 | 475373 | 475373 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTHER NEGOTIATED PROCUREMENT( BELOW 50K) | [23 empty] | N/A |  | N/A | N/A |  |  | N/A | [13 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR PRE-PROCUREMENT | [19 empty] | PROC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-02 | 2021-01-02 | N/A | 2021-01-02 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-10 | 2021-02-10 | GAA | 3000 | 3000 | 0 | 2800 | 2800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR PRE PROCUREMENT CONFORENCE NOV. 24 | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-23 | 2020-11-23 | N/A | 2020-11-23 | 2020-11-24 | 2020-11-24 | 2020-11-24 | 2020-11-24 | 2020-11-24 | GAA | 3300 | 3300 | 0 | 2530 | 2530 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR PRE-PROCUREMENT CONFERENCE OCTOBER 15, 2020 | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-10-14 | 2020-10-14 | N/A | 2020-10-14 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | GAA | 7500 | 7500 | 0 | 7125 | 7125 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR PRE-PROC CONFERENCE | [19 empty] | BAC | No | Small Value Procurement | N/A | 2021-01-14 | N/A | N/A | 2021-01-14 | 2021-01-14 | N/A | 2021-01-14 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-01-15 | GAA | 7500 | 7500 | 0 | 7125 | 7125 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AUTOMATICE ALCOHOL DISPENSER WITH STAND | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-06-09 | 2021-06-09 | GAA | 7500 | 7500 | 0 | 7440 | 7440 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| INK CARTRIDGE | [19 empty] | COA | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/16/2021 | 2/16/2021 | N/A | 2/16/2021 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-04 | 2021-03-04 | GAA | 7920 | 7920 | 0 | 5000 | 5000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR ORIENTATION OF RECORDS FOCAL PERSONS | [19 empty] | RECORDS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/17/2021 | 2/17/2021 | N/A | 2/17/2021 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | GAA | 8520 | 8520 | 0 | 8520 | 8520 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BARBED WIRE | [19 empty] | GP | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/15/2021 | 03/15/2021 | N/A | 03/15/2021 | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-14 | GAA | 8745 | 8745 | 0 | 8500 | 8500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE BID OPENING | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-25 | 2020-11-25 | N/A | 2020-11-25 | 2020-11-26 | 2020-11-26 | 2020-11-26 | 2020-11-26 | 2020-11-26 | GAA | 9900 | 9900 | 0 | 9394 | 9394 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY SUPPLIESFOR DEVELOPMENT OF LACTOBACILLUS INOCULANTS | [19 empty] | RDD FOR BURO BOOSTER | No | Small Value Procurement | N/A | 2021-03-13 | N/A | N/A | 4/16/2021 | 4/16/2021 | N/A | 4/16/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 | 2021-06-15 | 2021-06-15 | GAA | 10400 | 10400 | 0 | 8400 | 8400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| WEBCAM & HEADPHONES | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-28 | 2021-04-28 | N/A | 2021-04-28 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-06-08 | 2021-06-08 | GAA | 12000 | 12000 | 0 | 10290 | 10290 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SHADED NET | [19 empty] | GP | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | 2021-06-20 | 2021-06-20 | 2021-06-20 | 2021-05-27 | 2021-05-27 | GAA | 12500 | 12500 | 0 | 11750 | 11750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR NEW EMPLOYEE ORIENTATION | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-08-03 | 2021-08-03 | N/A | 2021-08-03 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-09 | 2021-03-09 | GAA | 12800 | 12800 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLIES FOR BURO BOOSTER PROJECT | [19 empty] | PSNS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-04 | 2020-12-04 | N/A | 2020-12-04 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-15 | 2021-01-15 | GAA | 12900 | 12900 | 0 | 12420 | 12420 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS AND SNACKS FOR SOCAIL PREPARATION TRAINING NIZ | [19 empty] | KMD-LECS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-09 | 2020-11-09 | N/A | 2020-11-09 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | GAA | 14000 | 14000 | 0 | 13300 | 13300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS PRE-BID CONFERENCE AND BID OPENING NOV. 27 AND DEC. 9, 2020 | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-26 | 2020-11-26 | N/A | 2020-11-26 | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2020-12-09 | 2020-12-09 | GAA | 14100 | 14100 | 0 | 13395 | 13395 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS ADVISORY BOARD MEETING | [19 empty] | PIMD | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-11-01 | 2021-11-01 | N/A | 2021-11-01 | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | GAA | 14250 | 14250 | 0 | 13725 | 13725 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REFRIGERATOR | [19 empty] | CRYO | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-30 | 2021-04-30 | N/A | 2021-04-30 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-06-19 | 2021-06-19 | GAA | 14500 | 14500 | 0 | 14175 | 14175 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS - WEBINAR VIEWING OF FARMER-CLIENTS | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-19 | 2020-11-19 | N/A | 2020-11-19 | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-01-20 | 2020-01-20 | GAA | 15000 | 15000 | 0 | 14250 | 14250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE PRE-BID CONFERENCE | [19 empty] | PROCUREMENT | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-02 | 2021-04-02 | N/A | 2021-04-02 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-22 | 2021-02-22 | GAA | 15000 | 15000 | 0 | 14250 | 14250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE PRE-BID CONFERENCE | [19 empty] | PROCUREMENT | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/17/2021 | 2/17/2021 | N/A | 2/17/2021 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-03-03 | 2021-03-03 | GAA | 15000 | 15000 | 0 | 14250 | 14250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| COMPACT DOCUMENT SCANNER | [19 empty] | RECORDS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-17 | 2020-11-17 | N/A | 2020-11-17 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2021-03-04 | 2021-03-04 | GAA | 15000 | 15000 | 0 | 13990 | 13990 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND ONSITE CALIBRATION OF CHEMICAL FUME HOOD CABINET | [19 empty] | BES | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-03 | 2021-03-03 | N/A | 2021-03-03 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-05-05 | 2021-05-05 | GAA | 15000 | 15000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HP CARTRIDGES | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-14 | 2021-05-14 | GAA | 15000 | 15000 | 0 | 14700 | 14700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FIELD & LABORATORY PPE'S | [19 empty] | GP | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-05-02 | 2021-05-02 | N/A | 2021-05-02 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-04-19 | 2021-04-19 | GAA | 15500 | 15500 | 0 | 14400 | 14400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS PRE-BID & BID OPENING | [19 empty] | PROC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-25 | 2021-01-25 | N/A | 2021-01-25 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2020-10-02 | 2020-10-02 | GAA | 15600 | 15600 | 0 | 14820 | 14820 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR HRMPSB | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/17/2021 | 2/17/2021 | N/A | 2/17/2021 | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-19 | 2021-02-19 | GAA | 15750 | 15750 | 0 | 14850 | 14850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ISOPROPYL ALCOHOL | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-22 | 2021-03-22 | N/A | 2021-03-22 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | GAA | 16000 | 16000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS AND SNACK FOR MILKYBUN PRODUCTION | [19 empty] | SEPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-04 | 2020-11-04 | N/A | 2020-11-04 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-04 | 2020-12-04 | GAA | 17000 | 17000 | 0 | 16145 | 16145 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BOOTH FOR THE VALENTINE'S DAY CELEBRATION | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-12-02 | 2021-12-02 | N/A | 2021-12-02 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | GAA | 18000 | 18000 | 0 | 18000 | 18000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SANCKS FOR THE 2021 HIGH VALUE CROPS WEEK | [19 empty] | OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/15/2021 | 4/15/2021 | N/A | 4/15/2021 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-04-16 | GAA | 18000 | 18000 | 0 | 17100 | 17100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ADDITIONAL PRINTING OF SIRE DIRECTORY | [19 empty] | ABGS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-15 | 2021-02-15 | N/A | 2021-02-15 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-05 | 2021-03-05 | GAA | 18135 | 18135 | 0 | 18135 | 18135 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRINTING OF TARPAULIN FOR GIG PROJECT | [19 empty] | RDD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-27 | 2020-11-27 | N/A | 2020-11-27 | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-02-03 | 2021-02-03 | GAA | 19000 | 19000 | 0 | 17795 | 17795 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR TECHNICAL CAUCUS (WASTE MANAGEMENT PRACTICES AND GROUND WATER QUALITY IN DAIRY BUFFALO FARMS IN NUEVA ECIJA) | [19 empty] | SEPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-10-03 | 2021-10-03 | N/A | 2021-10-03 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-11 | GAA | 19250 | 19250 | 0 | 18260 | 18260 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLIES AND MATERIALS FOR ADVISORY BOARD | [19 empty] | PIMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-03 | 2020-12-03 | N/A | 2020-12-03 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2020-11-18 | 2020-11-18 | GAA | 20000 | 20000 | 0 | 17700 | 17700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SNACKS FOR HRMS ACTIVITY | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-28 | 2021-01-28 | N/A | 2021-01-28 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2021-02-01 | GAA | 20000 | 20000 | 0 | 15800 | 15800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2TB EXTERNAL HARD DRIVE | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-02-08 | GAA | 20000 | 20000 | 0 | 18396 | 18396 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CONCEPT DESIGN AND PHOTOBOOTH FOR NATIONAL WOMEN'S MONTH | [19 empty] | ODED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | GAA | 20000 | 20000 | 0 | 20000 | 20000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| STORAGE BOXES & AIRGTIGHT CONTAINERS | [19 empty] | PDIS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-28 | 2021-01-28 | N/A | 2021-01-28 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-03-01 | 2021-03-01 | GAA | 21700 | 21700 | 0 | 21300 | 21300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TABLET AND MOBILE PHONE | [19 empty] | ICTS FOR OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-08 | 2021-04-08 | N/A | 2021-04-08 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-14 | 2021-05-14 | GAA | 23000 | 23000 | 0 | 22980 | 22980 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES | [19 empty] | NBDH-CBEDS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-04 | 2020-12-04 | N/A | 2020-12-04 | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-01-18 | 2021-01-18 | GAA | 23900 | 23900 | 0 | 12600 | 12600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS DURING PRE-PROCUREMENT CONFERENCE OCTOBER 27 AND NOV .16 | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-10-20 | 2020-10-20 | N/A | 2020-10-20 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-11-16 | 2020-11-16 | GAA | 24300 | 24300 | 0 | 20225 | 20225 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AUTOMATIC ALCOHOL DISPENSER AND THERMAL SCANNER WITH STAND | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-22 | 2021-03-22 | N/A | 2021-03-22 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-19 | 2021-04-19 | GAA | 25000 | 25000 | 0 | 21000 | 21000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TECHNICAL SERVICE OF LABTECH | [19 empty] | BES | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-28 | 2021-01-28 | N/A | 2021-01-28 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-03-17 | 2021-03-17 | GAA | 25200 | 25200 | 0 | 25200 | 25200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TOKENS AND ADDITIONAL MATERIALS | [19 empty] | PIMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-08-03 | 2021-08-03 | N/A | 2021-08-03 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | GAA | 26000 | 26000 | 0 | 26000 | 26000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TUBLESS TIRES 195 R14C | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-08 | 2021-03-08 | N/A | 2021-03-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | GAA | 27600 | 27600 | 0 | 23200 | 23200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MAINTENANCE OF 3TR AIRCON | [19 empty] | PSNS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-02 | 2020-12-02 | N/A | 2020-12-02 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-25 | 2021-01-25 | GAA | 30000 | 30000 | 0 | 29500 | 29500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS AND CALIBRATION OF MICROSCOPES AND STEREOSCOPE | [19 empty] | RPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-16 | 2020-12-16 | N/A | 2020-12-16 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-02-24 | 2021-02-24 | GAA | 30000 | 30000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TOKEN (JACKET) FOR THE LEARNING AND DEVELOPMENT PROGRAM | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-26 | 2021-02-26 | N/A | 2021-02-26 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-03-02 | 2021-03-02 | GAA | 30000 | 30000 | 0 | 24500 | 24500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE FY 2020 YEAR-END FINANCIAL ASSESSMENT OF BOOKS | [19 empty] | PROPERTY CHARGED TO ACCOUNTING | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-09-03 | 2021-09-03 | N/A | 2021-09-03 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-11 | 2021-03-11 | GAA | 30000 | 30000 | 0 | 28500 | 28500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SNACKS FOR SOCIAL PREPARATION TRAINING | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-10-03 | 2021-10-03 | N/A | 2021-10-03 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-12 | 2021-03-12 | GAA | 30000 | 30000 | 0 | 28500 | 28500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY SUPPLIES FOR DEVELOPMENT OF LACTOBACILLUS INOCULANTS | [19 empty] | RDD FOR BURO BOOSTER | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/16/2021 | 4/16/2021 | N/A | 4/16/2021 | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-05-31 | 2021-05-31 | GAA | 32380 | 32380 | 0 | 28065 | 28065 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TUBLESS TIRES 195 R15C | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-25 | 2021-01-25 | N/A | 2021-01-25 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | GAA | 34000 | 34000 | 0 | 26400 | 26400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS PCC VEHICLES SLG-860, SJJ-386 & SKY-605 | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/18/2021 | 2/18/2021 | N/A | 2/18/2021 | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-04 | 2021-03-04 | GAA | 34400 | 34400 | 0 | 32350 | 32350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED LANYARD | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-11 | 2021-03-11 | N/A | 2021-03-11 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-22 | 2021-04-22 | GAA | 35000 | 35000 | 0 | 33950 | 33950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CALIBRATION AND MAINTENANCE OF LABORATORY EQUIPMENTS | [19 empty] | CRYO | No | Small Value Procurement | N/A | 2020-10-22 | N/A | N/A | 2020-10-26 | 2020-10-26 | N/A | 2020-10-26 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-21 | 2021-01-21 | GAA | 35750 | 35750 | 0 | 22176 | 22176 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS AND SNACKS FOR THE LEARNING AND DEVELOPMENT PROGRAM 2021 | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-01 | 2021-03-01 | N/A | 2021-03-01 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-04 | 2021-03-04 | GAA | 36000 | 36000 | 0 | 35300 | 35300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SNOW FROSTED TINT | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/19/2021 | 4/19/2021 | N/A | 4/19/2021 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-17 | 2021-05-17 | GAA | 36000 | 36000 | 0 | 35500 | 35500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PERSONAL PROTECTIVE EQUIPMENT | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-20 | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-10 | 2021-06-10 | GAA | 38460 | 38460 | 0 | 28900 | 28900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CHILLER ONE DOOR SHOWCASE | [19 empty] | BES | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-19 | 2021-01-19 | N/A | 2021-01-19 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-03-02 | 2021-03-02 | GAA | 40000 | 40000 | 0 | 39500 | 39500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS & SNACKS FOR THE CONDUCT OF MFO SCOREBOARD VALIDATION | [19 empty] | PIMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-14 | 2020-12-14 | N/A | 2020-12-14 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-16 | 2020-12-16 | GAA | 42000 | 42000 | 0 | 39600 | 39600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR & MAINTENANCE OF PCC VEHICLES | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/14/2021 | 4/14/2021 | N/A | 4/14/2021 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | GAA | 42900 | 42900 | 0 | 42900 | 42900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED LEATHER SLEEVES FOR PLANNER | [19 empty] | OPERATIONS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-16 | 2021-02-16 | N/A | 2021-02-16 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-04-05 | 2021-04-05 | GAA | 43000 | 43000 | 0 | 43000 | 43000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MOBILE TABLET | [19 empty] | RDD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2/19/2021 | 2/19/2021 | N/A | 2/19/2021 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-19 | 2021-03-19 | GAA | 43500 | 43500 | 0 | 41970 | 41970 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-05-02 | 2021-05-02 | N/A | 2021-05-02 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-31 | 2021-03-31 | GAA | 43600 | 43600 | 0 | 41608 | 41608 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR & MAINTENANCE OF TOYOTA GL GRANDIA | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-12 | 2021-04-12 | N/A | 2021-04-12 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-03 | GAA | 44000 | 44000 | 0 | 44000 | 44000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3SMF BATTERY & 2SMF BATTERY | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | GAA | 46000 | 46000 | 0 | 43000 | 43000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS OF PCC VEHICLES SFJ-893, SFV-408 AND SJJ-409 | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-11 | 2020-12-11 | N/A | 2020-12-11 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | GAA | 46650 | 46650 | 0 | 40100 | 40100 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GRASS CUTTER | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-17 | 2021-03-17 | GAA | 47700 | 47700 | 0 | 44250 | 44250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED FACE MASKS | [19 empty] | OED-ANNIV | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | GAA | 48750 | 48750 | 0 | 48750 | 48750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR ORIENTATION AND CAPACITY BUILDING | [19 empty] | CBED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-12-04 | 2021-12-04 | N/A | 2021-12-04 | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-03-15 | 2021-03-15 | GAA | 49500 | 49500 | 0 | 46350 | 46350 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF PCC VEHICLES | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-03-22 | 2021-03-22 | N/A | 2021-03-22 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | GAA | 49835 | 49835 | 0 | 45635 | 45635 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CORPORATE PAPER BAGS | [19 empty] | OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-09 | 2020-11-09 | N/A | 2020-11-09 | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2020-12-17 | GAA | 50000 | 50000 | 0 | 46250 | 46250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CATERING SERVICES FOR VIRTUAL LAB TRAINING | [19 empty] | ABGS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-01-19 | 2021-01-19 | N/A | 2021-01-19 | 2021-01-25 | 2021-01-25 | 2021-01-25 | 2021-01-29 | 2021-01-29 | GAA | 50000 | 50000 | 0 | 42700 | 42700 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| STORAGE SUPPLIES | [19 empty] | CEDS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-13 | 2020-11-13 | N/A | 2020-11-13 | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-01-31 | 2021-01-31 | GAA | 50000 | 50000 | 0 | 37420 | 37420 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND CALIBRATION OF LAB EQUIPMENT (BES) | [19 empty] | BES | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/13/2021 | 4/13/2021 | N/A | 4/13/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 | 2021-05-21 | 2021-05-21 | GAA | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROFESSIONAL SERVICE FEE | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-16 | 2021-04-16 | N/A | 2021-04-16 | 2021-05-25 | 2021-05-25 | 2021-05-25 | 2021-05-27 | 2021-05-27 | GAA | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of Procurement Activities | [37 empty] | 14329374.7
Total Contract Price of Procurement Actitvites Conducted | [37 empty] | 11084604.38
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 3244770.32
0N-GOING PROCUREMENT ACTIVITIES
| BATTERY SEALED ACID AND VALIDATION OF ULTRA LOW LABORATORY FREEZER | [19 empty] | CRYO | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-10-02 | 2020-10-02 | N/A | 2020-10-02 | 2020-12-16 | 2020-12-16 | 2020-12-16 |  |  | GAA | 33000 | 33000 | 0 | 30240 | 30240 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FRAGEMENT AND SEQUENCE ANALYSIS | [19 empty] | CRYO | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-10-29 | 2020-10-29 | N/A | 2020-10-29 | 2020-12-22 | 2020-12-22 | 2020-12-22 |  |  | GAA | 100000 | 100000 | 0 | 21834 | 21834 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VETERINARY SUPPLIES FOR RRC | [19 empty] | BES | No | Small Value Procurement | N/A | 2020-08-08 | N/A | N/A | 2020-10-27 | 2020-10-27 | N/A | 2020-10-27 | 2021-02-17 | 2021-02-17 | 2021-02-17 |  |  | GAA | 229615 | 229615 | 0 | 100389 | 100389 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANNUAL RENEWAL SUBSCRIPTION OF ASREML | [19 empty] | ABGS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2020-11-10 | 2020-11-10 | N/A | 2020-11-10 | [5 empty] | GAA |  |  |  | 47996.81 | 47996.81 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AIRCONDITIONING UNITS FOR OED AND DED OFFICE | [19 empty] | GSS | No | Small Value Procurement | N/A | 2020-10-31 | N/A | N/A | 2020-11-16 | 2020-11-16 | N/A | 2020-11-16 | 2020-12-21 | 2020-12-21 | 2020-12-21 |  |  | GAA | 386859.2 | 386859.2 | 0 | 384652.8 | 384652.8 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MILK REPLACER | [19 empty] | PSNS | No | Small Value Procurement | N/A | 2020-10-06 | N/A | N/A | 2020-11-13 | 2020-11-13 | N/A | 2020-11-13 | 2021-01-21 | 2021-01-21 | 2021-01-21 |  |  | GAA | 255470 | 255470 | 0 | 19950 | 19950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| INSTALLATION OF VOLTAGE SURGE PROTECTOR OF DVMS AIRCON | [19 empty] | GSS | No | Emergency Case | N/A | N/A | N/A | N/A | 2020-11-24 | 2020-11-24 | N/A | 2020-11-24 | 2021-01-13 | 2021-01-13 | 2021-01-13 |  |  | GAA | 66158.4 | 66158.4 | 0 | 64964.68 | 64964.68 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LIQUID NITROGEN TANKS | [19 empty] | OPERATIONS/ABGS | No | Direct Contracting | N/A | 2020-11-24 | N/A | N/A | 2020-11-27 | 2020-11-27 | N/A | 2020-11-27 | 2021-01-11 | 2021-01-11 | 2021-01-11 |  |  | GAA | 236988 | 236988 | 0 | 225000 | 225000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS OFFIE EQUIPMENT AND CONSUMABLES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2020-10-21 | N/A | N/A | 2020-11-13 | 2020-11-13 | N/A | 2020-11-13 | 2021-01-14 | 2021-01-14 | 2021-01-14 |  |  | GAA | 54790 | 54790 | 0 | 51040 | 51040 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VETERINARY DRUGS, HORMONES AND SUPPLIES | [19 empty] | RPS | No | Small Value Procurement | N/A | 2020-10-22 | N/A | N/A | 2020-11-10 | 2020-11-10 | N/A | 2020-11-10 | 2021-01-18 | 2021-01-18 | 2021-01-18 |  |  | GAA | 333000 | 333000 | 0 | 42000 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HEMOSEP,ACEPROMAZINE | [19 empty] | BES | No | Small Value Procurement | N/A |  | N/A | N/A | 2020-11-10 | 2020-11-10 | N/A | 2020-11-10 | [5 empty] | GAA |  |  |  | 42000 | 42000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VETERINARY DRUGS, HORMONES AND SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2020-10-22 | N/A | N/A | 2020-11-10 | 2020-11-10 | N/A | 2020-11-10 | 2020-12-23 | 2020-12-23 | 2020-12-23 |  |  | GAA | 208800 | 208800 | 0 | 190032 | 190032 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY SUPPLIES FOR CENTER | [19 empty] | OPERATIONS | No | Small Value Procurement | N/A |  | N/A | N/A | 2020-11-18 | 2020-11-18 | N/A | 2020-11-18 | [5 empty] | GAA |  |  |  | 15290 | 15290 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MILKY BUN | [19 empty] | SEPS | No | Emergency Case | N/A |  | N/A | N/A | 2020-12-29 | 2020-12-29 | N/A | 2020-12-29 | [5 empty] | GAA |  |  |  | 35000 | 35000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR PRE-PROCUREMENT CONFERENCE (32 PAX) | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-10-26 | 2020-10-26 | N/A | 2020-10-26 | 2020-10-29 | 2020-10-29 | 2020-10-29 |  |  | GAA | 9600 | 9600 | 0 | 9120 | 9120 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS DURING PRE-PROCUREMENT CONFERENCE (19 PAX) | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-17 | 2020-11-17 | N/A | 2020-11-17 | 2020-11-18 | 2020-11-18 | 2020-11-18 |  |  | GAA | 5700 | 5700 | 0 | 5415 | 5415 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| AGRILTURAL SUPPLIES FOR BURO BOOSTER | [19 empty] | PSNS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-23 | 2020-11-23 | N/A | 2020-11-23 | 2021-01-21 | 2021-01-21 | 2021-01-21 |  |  | GAA | 50000 | 50000 | 0 | 47600 | 47600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FRAGMENT AND SEQUENCE ANALYSIS | [19 empty] | ABGS | No | Agency to Agency | N/A |  | N/A | N/A | 2020-12-04 | 2020-12-04 | N/A | 2020-12-04 | 2020-12-22 | 2020-12-22 | 2020-12-22 |  |  | GAA | 100000 | 100000 | 0 | 100000 | 100000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CLEANING SUPPLIES | [19 empty] | NPIG | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-10 | 2020-12-10 | N/A | 2020-12-10 | 2021-01-13 | 2021-01-13 | 2021-01-13 |  |  | GAA | 26200 | 26200 | 0 | 21150 | 21150 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| JAPANESE PAPER AND CELLOPHANE CLEAR | [19 empty] | CDCPF | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-10 | 2020-12-10 | N/A | 2020-12-10 | 2021-01-11 | 2021-01-11 | 2021-01-11 |  |  | GAA | 29000 | 29000 | 0 | 23850 | 23850 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FOSS COMBI MILK ANALYZER | [19 empty] | ABGS | No | SMall Value Procurement | N/A | N/A | N/A | N/A | 2020-12-10 | 2020-12-10 | N/A | 2020-12-10 | 2021-01-27 | 2021-01-27 | 2021-01-27 |  |  | GAA | 284000 | 284000 | 0 | 260731.1 | 260731 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS PRE-BID CONFERENCE AND BID OPENING DECEMBER 4 AND DEC 16 | [19 empty] | BAC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-12-03 | 2020-12-03 | N/A | 2020-12-03 | 2020-12-04 | 2020-12-04 | 2020-12-04 |  |  | GAA | 14650 | 14650 | 0 | 13906 | 13906 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE MEETING AND 2020 ANNUAL SUPPLIER'S FORUM DEC. 11, 2020 | [19 empty] | PROCUREMENT | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2020-11-24 | 2020-11-24 | N/A | 2020-11-24 | 2020-11-25 | 2020-11-25 | 2020-11-25 |  |  | GAA | 12500 | 12500 | 0 | 12450 | 12450 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| JMP SOFTWARE ANNUAL SUBSCRIPTION | [19 empty] | ABGS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-19 | 2021-01-19 | N/A | 2021-01-19 | 2021-02-23 | 2021-02-23 | 2021-02-23 |  |  | GAA | 55000 | 55000 | 0 | 54208 | 54208 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BIOTIUM NUCLEIC ACID GEL STAIN | [19 empty] | CRYO | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-03-15 | 2021-03-15 | 2021-03-15 |  |  | GAA | 14920 | 14920 | 0 | 13172 | 13172 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SPECIFIC FOSS CONSUMABLES | [19 empty] | ABGS | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-23 | 2021-02-23 | 2021-02-23 |  |  | GAA | 771092 | 771092 | 0 | 658825.58 | 658825.58 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SPECIFIC BOVINE-RELATED KITS | [19 empty] | BES | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-18 | 2021-02-18 | 2021-02-18 |  |  | GAA | 211926 | 211926 | 0 | 211296 | 211296 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PETRIFILMS | [19 empty] | BES | Yes | Direct Contracting | N/A | N/A | N/A | N/A | 2021-01-07 | 2021-01-07 | N/A | 2021-01-07 | 2021-02-23 | 2021-02-23 | 2021-02-23 |  |  | GAA | 262790 | 262790 | 0 | 230112 | 230112 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF HYUNDAI STAREX VAN (SKW-941) | [19 empty] | GSS | No | Emergency Case | N/A | N/A | N/A | N/A | 2021-01-26 | 2021-01-26 | N/A | 2021-01-26 | [5 empty] | GAA | 253154.25 | 253154.25 | 0 | 253154.25 | 253154.25 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PMS & CALIBRATION OF VARIOUS INCUBATOR | [19 empty] | RPS | No | Small Value Procurement | N/A | 2021-01-20 | N/A | N/A | 2021-01-02 | 2021-01-02 | N/A | 2021-01-02 | 2021-02-23 | 2021-02-23 | 2021-02-23 |  |  | GAA | 50000 | 50000 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY CHEMICALS AND REAGENT | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-04-29 | 2021-04-29 | 2021-04-29 |  |  | GAA | 565176.5 | 565176.5 | 0 | 319800 | 319800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VETERINARY DRUG SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-09-02 | 2021-09-02 | N/A | 2021-09-02 | 2021-03-05 | 2021-03-05 | 2021-03-05 |  |  | GAA | 609876 | 609876 | 0 | 26070 | 26070 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRINTING ANNUAL REPORT 2019-2020 | [19 empty] | HRMS | No | Small Value Procurement | N/A |  | N/A | N/A | 2/16/2021 | 2/16/2021 | N/A | 2/16/2021 | 2021-03-11 | 2021-03-11 | 2021-03-11 |  |  | GAA | 122695.5 | 122695.5 | 0 | 122695.5 | 122695.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| STRATEGIC PLAN & WORKSHOP | [19 empty] | RDD | No | Small Value Procurement | N/A |  | N/A | N/A | 2/17/2021 | 2/17/2021 | N/A | 2/17/2021 | 2021-02-18 | 2021-02-18 | 2021-02-18 |  |  | GAA | 39000 | 39000 | 0 | 36900 | 36900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ICT EQUIPMENT | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-03-22 | 2021-03-22 | 2021-03-22 |  |  | GAA | 220000 | 220000 | 0 | 195000 | 195000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-01-28 | N/A | N/A | 2021-02-19 | 2021-02-19 | N/A | 2021-02-19 | 2021-04-19 | 2021-04-19 | 2021-04-19 |  |  | GAA | 442600.56 | 442600.56 | 0 | 174536 | 174536 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND CALIBRATION OF BES EQUIPMENT | [19 empty] | BES | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | [5 empty] | GAA | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF STEP ONE PLUS REAL TIME PCR SYSTEM | [19 empty] | RPS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-03-30 | 2021-03-30 | 2021-03-30 |  |  | GAA | 165000 | 165000 | 0 | 165000 | 165000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GAD ADVOCACY ITEMS | [19 empty] | ODED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-04-06 | 2021-04-06 | 2021-04-06 |  |  | GAA | 33000 | 33000 | 0 | 33000 | 33000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES NOT AVAILABLE IN PS-DBM | [19 empty] | VARIOUS | No | Shopping(b) | N/A | 2021-01-30 | N/A | N/A | 2021-02-19 | 2021-02-19 | N/A | 2021-02-19 | 2021-04-08 | 2021-04-08 | 2021-04-08 |  |  | GAA | 636085.16 | 636085.16 | 0 | 629711.16 | 629711.16 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR TECHNICAL CAUCUS ON FEB. 24, 2021 | [19 empty] | RDD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-02-23 | 2021-02-23 | N/A | 2021-02-23 | 2021-02-24 | 2021-02-24 | 2021-02-24 |  |  | GAA | 9000 | 9000 | 0 | 8750 | 8750 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LABORATORY CHEMICALS AND REAGENT | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-02-24 | 2021-02-24 | N/A | 2021-02-24 | 2021-04-15 | 2021-04-15 | 2021-04-15 |  |  | GAA | 7590 | 7590 | 0 | 6900 | 6900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED VIRTUAL TOUR PROJECT FOR PCC | [19 empty] | KMD | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | 2021-06-08 | 2021-06-08 | 2021-06-08 |  |  | GAA | 450000 | 450000 | 0 | 250000 | 250000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| INSTALLATION OF TWO GLASS DOORS AT THE OFFICE OF THE EXECUTIVE DIRECTOR AND OFFICE OF THE DEPUTY EXECUTIVE DIRECTOR | [19 empty] | GSS | No | SMall Value Procurement | N/A | N/A | N/A | N/A | 2021-10-03 | 2021-10-03 | N/A | 2021-10-03 | 2021-05-04 | 2021-05-04 | 2021-05-04 |  |  | GAA | 16000 | 16000 |  | 13830 | 13830 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE PRE-BID CONFERENCE | [19 empty] | PROC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | 2021-03-19 | 2021-03-19 | 2021-03-19 |  |  | GAA | 15000 | 15000 | 0 | 14250 | 14250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| KNAPSACK SPRAYER | [19 empty] | PSNS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | [5 empty] | GAA |  |  |  | 6800 | 6800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES FOR BURO BOOSTER PROJECT | [19 empty] | PSNS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 |  |  | GAA | 21270 | 21270 | 0 | 21270 | 21270 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SUPPLIES FOR GENEPOOL OPERATIONS | [19 empty] | GP | No | Small Value Procurement | N/A | 2021-02-17 | N/A | N/A | 03/19/2021 | 03/19/2021 | N/A | 03/19/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 |  |  | GAA | 80400 | 80400 | 0 | 78540 | 78540 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND CALIBRATION OF VARIOUS MICROSCOPES AND MICROPLATE ELISA READER | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-03-23 | 2021-03-23 | N/A | 2021-03-23 | 2021-05-10 | 2021-05-10 | 2021-05-10 |  |  | GAA | 22500 | 22500 | 0 | 22500 | 22500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF TWO 5TR INVERTER AIRCON | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-03-17 | N/A | N/A | 2021-03-25 | 2021-03-25 | N/A | 2021-03-25 | 2021-04-20 | 2021-04-20 | 2021-04-20 |  |  | GAA | 112848.74 | 112848.74 | 0 | 111372.8 | 111372.8 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| EMERGENCY PURCHASE OF EIGHT (8) LED WALL POWER SUPPLY AND ONE (1) 20KVA AVR | [20 empty] | No | Emergency Case | N/A | N/A | N/A | N/A | 3/29/21 | 3/29/21 | N/A | 3/29/21 | 2021-05-11 | 2021-05-11 | 2021-05-11 |  |  | GAA | 51000 | 51000 | 0 | 51000 | 51000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS IT SUPPLIES | [19 empty] | ICTS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-08 | 2021-04-08 | N/A | 2021-04-08 | [5 empty] | GAA |  |  |  | 382170 | 382170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS IT SUPPLIES | [19 empty] | ICTS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-08 | 2021-04-08 | N/A | 2021-04-08 | [5 empty] | GAA |  |  |  | 119030 | 119030 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 4-PORT USB EXTENSION PORT....USB-C HDMI VGA ADAPTER | [19 empty] | ICTS | No | Small Value Procurement | N/A | 2021-01-30 | N/A | N/A | 2021-04-07 | 2021-04-07 | N/A | 2021-04-07 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  | GAA | 710010 | 710010 | 0 | 382170 | 382170 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE ORIENTATION OTC-PPE | [19 empty] | PROPERTY | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-04 | 2021-05-04 | N/A | 2021-05-04 | 2021-04-05 | 2021-04-05 | 2021-04-05 |  |  | GAA | 44000 | 44000 | 0 | 41800 | 41800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FRAGMENT ANALYSIS | [19 empty] | CRYO | No | Small Value Procurement | N/A | 2021-04-09 | N/A | N/A | 2021-12-04 | 2021-12-04 | N/A | 2021-12-04 | 2021-05-07 | 2021-05-07 | 2021-05-07 |  |  | GAA | 150000 | 150000 | 0 | 148950 | 148950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF AUTOCLAVE | [19 empty] | ABGS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/13/2021 | 4/13/2021 | N/A | 4/13/2021 | 2021-05-10 | 2021-05-10 | 2021-05-10 |  |  | GAA | 35850 | 35850 | 0 | 35600 | 35600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DNA SEQUENCING SERVICE | [19 empty] | CRYO | No | Small Value Procurement | N/A | 2021-04-09 | N/A | N/A | 4/13/2021 | 4/13/2021 | N/A | 4/13/2021 | 44323 | 44323 | 44323 |  |  | GAA | 198000 | 198000 | 0 | 143420 | 143420 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE PRE-BID CONFERENCE | [19 empty] | PROC | No | Small Value Procurement | N/A | N/A | N/A | N/A | 3/25/2021 | 3/25/2021 | N/A | 3/25/2021 | 2021-03-25 | 2021-03-25 | 2021-03-25 |  |  | GAA | 15000 | 15000 | 0 | 14250 | 14250 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE BID OPENING | [19 empty] | PROC | No | Small Value Procurement | N/A |  | N/A | N/A | 3/30/2021 | 3/30/2021 | N/A | 3/30/2021 | 2021-03-30 | 2021-03-30 | 2021-03-30 |  |  | GAA | 22500 | 22500 | 0 | 21375 | 21375 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TONER FOR KONICA DEVELOP INEO | [19 empty] | VARIOUS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-08-04 | 2021-08-04 | N/A | 2021-08-04 | [5 empty] | GAA |  |  |  | 147300 | 147300 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS AND SNACKS FOR THE CREATION OF SPECIAL RESOURCE MERIT PROMOTION AND SELECTION BOARD (SHRMPSB) AND ITS COMPOSITION FOR THE SELECTION OF EXECUTIVE DIRECTOR III | [19 empty] | OED/HRMS | No | SMAll Value Procurement | N/A | N/A | N/A | N/A | 2021-07-04 | 2021-07-04 | N/A | 2021-07-04 | 2021-04-07 | 2021-04-07 | 2021-04-07 |  |  | GAA | 40950 | 40950 | 0 | 19215 | 19215 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR THE IMS RE-CERTIFICATION AUDIT | [19 empty] | MSAO | No | Small Value Procurement | N/A | N/A | N/A | N/A | 3/17/2021 | 3/17/2021 | N/A | 3/17/2021 | 2021-03-17 | 2021-03-17 | 2021-03-17 |  |  | GAA | 40200 | 40200 | 0 | 38190 | 38190 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GPI MILK BOTTLES, ROUND, 100ML | [19 empty] | RDD FOR BURO BOOSTER | No | Small Value Procurement | N/A | 2021-03-13 | N/A | N/A | 4/16/2021 | 4/16/2021 | N/A | 4/16/2021 | 2021-06-08 | 2021-06-08 | 2021-06-08 |  |  | GAA | 11000 | 11000 | 0 | 9900 | 9900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| FABRICATED CUSTOMIZED CONICAL TUBES AND CAPS SET 40ML SAMPLE BOTTLE FOR MILK FEEDING | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-10 | 2021-05-10 | 2021-05-10 |  |  | GAA | 140000 | 140000 | 0 | 115000 | 115000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DRUM FOR COPIER | [19 empty] | HRMS | No | Direct Contracting | N/A |  | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | [5 empty] | GAA |  |  |  | 9500 | 9500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ACRYCLIC OFFICE NAME PLATE | [19 empty] | HRMS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-03 | 2021-05-03 | 2021-05-03 |  |  | GAA | 6000 | 6000 | 0 | 5550 | 5550 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| INSTALLATION OF SIGNAGE | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-04-14 | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-03 | 2021-05-03 | 2021-05-03 |  |  | GAA | 150000 | 150000 | 0 | 87500 | 87500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GIEMA STAIN | [19 empty] | RPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/21/2021 | 4/21/2021 | N/A | 4/21/2021 | 2021-05-06 | 2021-05-06 | 2021-05-06 |  |  | GAA | 45000 | 45000 | 0 | 33930 | 33930 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED CERTIFICATE HOLDER WITH BLANK COVER | [19 empty] | OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | [5 empty] | GAA |  |  |  | 29000 | 29000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GLASS PLAQUE & CUSTOMIZED TOTE BAG | [19 empty] | OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 4/20/2021 | 4/20/2021 | N/A | 4/20/2021 | 2021-05-07 | 2021-05-07 | 2021-05-07 |  |  | GAA | 43000 | 43000 | 0 | 36000 | 36000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEDICINES AND MEDICAL SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-04-22 | 2021-04-22 | N/A | 2021-04-22 | [5 empty] | GAA |  |  |  | 114968.5 | 114968.5 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MILK CAN, STAINLESS STEEL, SEAMLESS INTERIOR, WITH LID AND HANDLE, 10-L CAPACITY | [19 empty] | CBED | No | Small Value Procurement | N/A | 2021-03-18 | N/A | N/A | 2021-04-23 | 2021-04-23 | N/A | 2021-04-23 | 2021-06-21 | 2021-06-21 | 2021-06-21 |  |  | GAA | 843300 | 843300 | 0 | 421000 | 421000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MILK PAIL, STAINLESS STEEL, SEAMLESS INTERIOR....HEAVY DUTY SILAGE BAG | [19 empty] | CBED | No | Small Value Procurement | N/A | 2021-03-18 | N/A | N/A | 2021-04-23 | 2021-04-23 | N/A | 2021-04-23 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  |  | GAA | 843300 | 843300 | 0 | 343985 | 343985 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS SUPPLIERS FOR REGIONAL CENTERS | [19 empty] | CBED | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-23 | 2021-04-23 | N/A | 2021-04-23 | [5 empty] | GAA |  |  |  | 343985 | 343985 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| SOFT RUBBER SPAGHETTI FLOOR MAT 4FT X 1FT...PUSH BRUSH | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | 2021-05-25 | 2021-05-25 | 2021-05-25 |  |  | GAA | 103115.89 | 103115.89 | 0 | 75376 | 75376 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS OFFICE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-26 | 2021-04-26 | N/A | 2021-04-26 | [5 empty] | GAA |  |  |  | 151637.25 | 151637.25 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS OFFICE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-26 | 2021-04-26 | N/A | 2021-04-26 | [5 empty] | GAA |  |  |  | 13516 | 13516 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| VARIOUS OFFICE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | [5 empty] | GAA |  |  |  | 34380 | 34380 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RAINCOAT, PONCHO STYLE, ASSORTED COLOR...SAFETY SHOES WITH STEEL TOE | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-20 | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | 2021-05-31 | 2021-05-31 | 2021-05-31 |  |  | GAA | 90450 | 90450 | 0 | 30000 | 30000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| EMERGENCY REPAIR & REPLACEMENT OF BATTERY FOR HYUNDAI STAREX VAN (SKW-941) | [19 empty] | GSS | No | Emergency Case | N/A | N/A | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | [5 empty] | GAA | 16095.25 | 16095.25 | 0 | 16095.25 | 16095.25 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| L-SHAPED METAL LEG TABLE WITH BUILT-IN PEDESTAL | [19 empty] | RDD | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-04-30 | 2021-04-30 | N/A | 2021-04-30 | 2021-06-07 | 2021-06-07 | 2021-06-07 |  |  | GAA | 56000 | 56000 | 0 | 55320 | 55320 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRINTING AND DELIVERY OF MONOGRAPH | [19 empty] | KMD | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | [5 empty] | GAA |  |  |  | 43950 | 43950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| JANITORIAL SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | [5 empty] | GAA |  |  |  | 49860 | 49860 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| JANITORIAL SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | [5 empty] | GAA |  |  |  | 6240 | 6240 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| JANITORIAL SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-30 | 2021-04-30 | N/A | 2021-04-30 | [5 empty] | GAA |  |  |  | 36200 | 36200 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CUSTOMIZED LETTERHEADS | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-20 | N/A | N/A | 2021-05-04 | 2021-05-04 | N/A | 2021-05-04 | [5 empty] | GAA | 50600 | 50600 | 0 | 45080 | 45080 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROFESSIONAL SERVICE FEE FOR INTERIOR FIT-OUT DESIGN CONCEPT DEVELOPMENT FOR PCC NHQ KNOWLEDGE BOOTH | [19 empty] | KMD | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-04 | 2021-05-04 | N/A | 2021-05-04 | [5 empty] | GAA |  |  |  | 25000 | 25000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| CAMERAL AND LAPEL RENTAL | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-05 | 2021-05-05 | N/A | 2021-05-05 | [5 empty] | GAA | 20000 | 20000 | 0 | 15000 | 15000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANTIBODIES | [19 empty] | RDD | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | [5 empty] | GAA |  |  |  | 89600 | 89600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ANNUAL CALIBRATION OF EQUIPMENT | [19 empty] | RPS | No | Small Value Procurement | N/A | 2021-04-21 | N/A | N/A | 2021-05-05 | 2021-05-05 | N/A | 2021-05-05 | [5 empty] | GAA | 127000 | 127000 | 0 | 127000 | 127000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFCIE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-03 | 2021-05-03 | N/A | 2021-05-03 | [5 empty] | GAA |  |  |  | 138708.91 | 138708.91 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR AND MAINTENANCE OF PCC VEHICLES | [19 empty] | GSS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-04-29 | 2021-04-29 | N/A | 2021-04-29 | [5 empty] | GAA |  |  |  | 39600 | 39600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE OF ISUZU D-MAX SKD-169 | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-06 | 2021-05-06 | N/A | 2021-05-06 | [5 empty] | GAA | 33639 | 33639 | 0 | 33639 | 33639 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PACKAGINGA AND STORAGE SUPPLIES | [19 empty] | VARIOUS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-06 | 2021-05-06 | N/A | 2021-05-06 | [5 empty] | GAA |  |  |  | 112852 | 112852 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GPI MILK BOTTLES SET, HDPE, ROUND, 1000ML | [19 empty] | PSNS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-06 | 2021-05-06 | N/A | 2021-05-06 | [5 empty] | GAA |  |  |  | 4950 | 4950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROFESSIONAL SERVICE FEE FOR BASIC LINUX TRAINING | [20 empty] | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-07-05 | 2021-07-05 | N/A | 2021-07-05 | [5 empty] | GAA |  |  |  | 50000 | 50000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROFESSIONAL SERVICE FEE FOR INTERIOR FIT-OUT DESIGN CONCEPT DEVELOPMENT FOR PCC NHQ KNOWLEDGE BOOTH | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-04 | 2021-05-04 | N/A | 2021-05-04 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  |  | GAA | 30000 | 30000 | 0 | 25000 | 25000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BIO RAD ABD | [19 empty] | BES | No | Small Value Procurement | N/A | 2021-05-01 | N/A | N/A | 2021-05-05 | 2021-05-05 | N/A | 2021-05-05 | 2021-06-21 | 2021-06-21 | 2021-06-21 |  |  | GAA | 100000 | 100000 | 0 | 89600 | 89600 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BALLPEN...TAPE FLAGS | [19 empty] | VARIOUS | No | Shopping(b) | N/A | 2021-04-17 | N/A | N/A | 2021-05-05 | 2021-05-05 | N/A | 2021-05-05 | 2021-05-31 | 2021-05-31 | 2021-05-31 |  |  | GAA | 153686.76 | 153686.76 | 0 | 142586.55 | 142586.55 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GPI MILK BOTTLES SET, HDPE, ROUND, 100ML | [19 empty] | PSNS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-05-06 | 2021-05-06 | N/A | 2021-05-06 | 2021-05-25 | 2021-05-25 | 2021-05-25 |  |  | GAA | 5500 | 5500 | 0 | 4950 | 4950 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| LIVESTREAMING SET UP | [19 empty] | OED | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-10 | 2021-05-10 | N/A | 2021-05-10 | [5 empty] | GAA | 50000 | 50000 | 0 | 49900 | 49900 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BAG CLOSER THREAD, 6 PLY, 100 METERS | [19 empty] | VARIOUS | No | Small Value Procurement | N/A | 2021-04-17 | N/A | N/A | 2021-05-10 | 2021-05-10 | N/A | 2021-05-10 | 2021-05-27 | 2021-05-27 | 2021-05-27 |  |  | GAA | 73400 | 73400 | 0 | 59050 | 59050 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR AND MAINTENANCE OF L200 FB VAN | [19 empty] | GSS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-12 | 2021-05-12 | N/A | 2021-05-12 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  | GAA | 75000 | 75000 | 0 | 38000 | 38000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE SKY-635 | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-07 | 2021-05-07 | N/A | 2021-05-07 | [5 empty] | GAA | 17058.76 | 17058.76 | 0 | 17058.76 | 17058.76 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE SKD-169 | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-17 | 2021-05-17 | N/A | 2021-05-17 | [5 empty] | GAA | 21946 | 21946 | 0 | 21946 | 21946 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| TIRE 8.25 -20 | [19 empty] | GSS | No | Small Value Procurement | N/A |  | N/A | N/A | 2021-05-12 | 2021-05-12 | N/A | 2021-05-12 | [5 empty] | GAA |  |  |  | 48990 | 48990 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DNA BASER ASSEMBLER | [19 empty] | CRYO | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-12 | 2021-05-12 | N/A | 2021-05-12 | 2021-06-01 | 2021-06-01 | 2021-06-01 |  |  | GAA | 35000 | 35000 | 0 | 30871.36 | 30871.36 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| MEALS FOR ORGANIZATIONAL ENTERPRISE CAPACITY BUILDING | [19 empty] | SEPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-20 | 2021-05-20 | N/A | 2021-05-20 | [5 empty] | GAA | 24000 | 24000 | 0 | 22800 | 22800 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROFESSIONAL SERVICE PROVIDER FOR ADMINISTRATIVE AND MANAGEMENT DATABASE SYSTEM | [19 empty] | MITHI | No | Small Value Procurement | N/A | 2021-05-06 | N/A | N/A | 2021-05-20 | 2021-05-20 | N/A | 2021-05-20 | 2021-06-07 | 2021-06-07 | 2021-06-07 |  |  | GAA-MITHI | 600000 | 600000 | 0 | 500000 | 500000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PEREVENTIVE MAINTENANCE SERVICE FOR HYUNDAI STAREX VAN | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-20 | 2021-05-20 | N/A | 2021-05-20 | 2021-06-15 | 2021-06-15 | 2021-06-15 |  |  | GAA | 500000 | 500000 | 0 | 102836.37 | 102836.37 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE SERVICE FOR HYUNDAI STAREX VAN (SKW-912) | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-20 | 2021-05-20 | N/A | 2021-05-20 | [5 empty] | GAA | 102836.37 | 102836.37 | 0 | 102836.37 | 102836.37 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRIMERS | [19 empty] | ABGS | No | Small Value Procurement | N/A | 2021-05-20 | N/A | N/A | 2021-05-25 | 2021-05-25 | N/A | 2021-05-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 |  |  | GAA | 117720 | 117720 | 0 | 117720 | 117720 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PRIMERS | [19 empty] | ABGS | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-05-25 | 2021-05-25 | N/A | 2021-05-25 | [5 empty] | GAA | 117720 | 117720 | 0 | 117720 | 117720 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE AND CALIBRATION OF BIOTEK EPOCH ELOSA READER | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-05-25 | 2021-05-25 | N/A | 2021-05-25 | [5 empty] | GAA | 40000 | 40000 | 0 | 40000 | 40000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PHILIPPINE FLAGLETS, FLAG, STICKER MARKER, BACKDROP | [19 empty] | KMD | No | Small Value Procurement | N/A | N/A | N/A | N/A | 2021-06-01 | 2021-06-01 | N/A | 2021-06-01 | [5 empty] | GAA | 17890 | 17890 | 0 | 16280 | 16280 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENNACE AND SUPPLY OF PARTS FOR SMART2PURE WATER PURIFICATION SYSTEM | [19 empty] | PSNS | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-06-08 | 2021-06-08 | N/A | 2021-06-08 | [5 empty] | GAA | 95512 | 95512 | 0 | 91936.4 | 91936.4 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| ESCO PHILIPPINES, INC. | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-06-10 | 2021-06-10 | N/A | 2021-06-10 | [5 empty] | GAA | 45360 | 45360 | 0 | 45360 | 45360 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PREVENTIVE MAINTENANCE OF LYOPHILIZER ABD CO2 INCUBATOR | [19 empty] | BES | No | Direct Contracting | N/A | N/A | N/A | N/A | 2021-06-10 | 2021-06-10 | N/A | 2021-06-10 | [5 empty] | GAA | 492128 | 492128 | 0 | 492128 | 492128 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF VEHICLE | [19 empty] | GSS | No | Direct Contracting | N/A | N/A | N/A | N/A |  |  | N/A | [6 empty] | GAA |  |  |  | 64707 | 64707 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| OFFICE SUPPLIES | [19 empty] | PIMD | No | Small Value Procurement | N/A |  | N/A | N/A |  |  | N/A | [6 empty] | GAA |  |  |  | 14400 | 14400 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HRMS EVENT SERVICES | [19 empty] | HRMS | No | Small Value Procurement | N/A |  | N/A | N/A |  |  | N/A | [6 empty] | GAA |  |  |  | 45500 | 45500 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RE-CERTICICATION AUDIT | [19 empty] | MSAO | No | Small Value Procurement | N/A |  | N/A | N/A |  |  | N/A | [6 empty] | GAA |  |  |  | 360000 | 360000 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REPAIR OF RAW HOUSE NO. 8 | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-02-03 | N/A | N/A | 02/17/2021 | 02/17/2021 | N/A | 02/17/2021 | 44244 | 44244 | 44244 |  |  | GAA | 110001 | 110001 | 0 | 107631.72 | 107631.72 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| REHABILITATION OF PROPERTY WAREHOUSE | [19 empty] | GSS | No | Small Value Procurement | N/A | 2021-03-16 | N/A | N/A | 2021-12-04 | 2021-12-04 | N/A | 2021-12-04 | 2021-04-12 | 2021-04-12 | 2021-04-12 |  |  | GAA | 148076.32 | 148076.32 | 0 | 146786.92 | 146786.92 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 14532100.66
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | NOEMI V. BALAIS | [10 empty] | ERIC P. PALACPAC | [10 empty] | RONNIE D. DOMINGO
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity